## Sheet1
Asumptions is we got AWS and GitHub acces
Tasks | Efforts in days
Update the code base with latest changes | 1
Optimize the code for more dynamic automation | 2
Setting up customer repository | 0.5
Check the Role has all necessary access | 0.5
Push the Images to customer AWS ECR and checks | 1
Update the code based on Customer Requiremnent | 1
Raise a PR and Validate the Terraform Plan | 0.5
Trobleshoot and fixes based on Plan and Customer environment | 2
Deployment | 1
Sanity Checks and Updation | 2
Handover and Sign off | 1
Total | 12.5